Holiday Charity Event Playbook

Organizing a successful holiday charity event that includes a silent auction, live auction, chance raffle, raffle, and cork pull requires meticulous planning and seamless execution. Below is a comprehensive playbook to help you manage the event effectively.

1. Event Concept and Objective

Goal Setting

- Primary Goal: Raise funds for GBTA Upstate NY Chapter.

- Secondary Goals: Raise funds for charity (specify amount or percentage goal).

- Audience: Members and Guests of GBTA Upstate NY Chapter.

2. Budgeting

Define Budget Categories:

- Venue: Rent or donation for the event space (or virtual platform cost).

- Food & Beverages: Dinner selection, appetizers, bar costs

- Event Decor: Holiday-themed decor, lighting, and signage.

- Promotions: Marketing materials (invitations, flyers, social media ads).

- Auction Items: Procurement costs for auction items.

- Entertainment/Activities: Music, guest speakers, hosts.

- Miscellaneous: Printing, volunteer needs, and additional overhead.

3. Event Planning Timeline

6-7 Months Before the Event:

- Venue Selection: Confirm the location, whether in-person or virtual.

- Theme & Branding: Finalize the holiday theme and design event materials.

- Vendor Selection: Catering, AV, security, photographers, decorators, etc.

- Secure Hotel – potential room rate for hotel nearby

8 to 12  Weeks Before the Event:

- Auction Item Procurement: Secure donations for silent/live auctions, cork pull, and raffle items. Goal of 50 plus individual items.

- Invite Guests: Send out invitations to membership and email list.

- Begin Promotion: Social media, email campaigns, press releases.

- Event Program: Finalize the schedule for the event, including auction times, raffle drawings, etc.

- Create Event Website/Registration Page: Enable ticket sales and RSVPs including food choices for dinner for egistration.

- Create Master Excel file of all donation items – Update donation list regularly and communicate to all board members.

- Make determination of start and stop times for Cocktails, Dinner, Auctions and Raffles.

- Traditionally –

Cocktails – 5:00, Dinner 6:00, End Silent Auction 7:15, Live Auction 7:30 finally pull Raffle tickets.

Promote event during current year chapter meetings

2-4 Weeks Before the Event:

- Finalize Auction Items: Set up the catalog for silent/live auctions, ensure they are well-documented.

- Prepare Raffle & Cork Pull Prizes: Procure unique or valuable prizes for these activities.

- Volunteer Training: Ensure volunteers are trained on responsibilities for auctions, raffles, and event logistics.

- Send Reminder invites

1 Week Before the Event:

- Confirm Event Logistics: Confirm catering, sound systems, and all vendors.

- Finalize Guest List: Double-check RSVP list.

- Final Promotions: Last-minute reminders through emails, social media, and event platforms.

4. Key Event Components

Silent Auction

- Setup:

  - Create signage related to each item in silents auction and bring to event.

  - Organize items on auction tables

  - Use bid sheets for tracking bids.

- Execution:

  - Designate a section of the venue or digital platform for the silent auction.

  - Set a start and end time (allow 1-2 hours for bidding).

  - Announce bid closing with a countdown.

- Tips:

  - Highlight exclusive or high-value items to generate interest.

  - Ensure clear instructions on how guests can place bids.

Live Auction

- Setup:

  - Select high-value or unique items for the live auction (e.g., vacation packages, luxury items, VIP experiences).

  - Have an experienced auctioneer or charismatic host to facilitate the bidding.

- Execution:

  - Auction items are displayed and described in a lively, engaging way.

  - Bidders raise hands or use a paddle to place bids.

  - Have a spotter to assist in managing bids.

- Tips:

  - Engage the crowd with teasers around the items.

  - Create a sense of urgency to drive up bids.

Chance Raffle

- Setup:

  - Gather raffle prizes (e.g., tech gadgets, gift certificates, vacation stays).

  - Sell raffle tickets at the event or online in advance.

- Execution:

  - Announce the raffle drawing time.

  - Use bags for raffle tickets.

  - Have a separate location or virtual drawing system.

  - Draw winners in a transparent and fair manner.

- Tips:

  - Use a "mystery prize" theme to make the raffle even more exciting.

  - Consider tiered pricing for raffle tickets (e.g., 1 for $10, 3 for $25).

Regular Raffle

- Setup:

  - Smaller prizes for this category, such as gift baskets, restaurant vouchers, and smaller luxury items.

  - Similar to the chance raffle but typically with more affordable items.

- Execution:

  - Ensure you have a system for drawing winners (ticket drum or digital).

  - Have a specific time during the event to call out raffle winners.

- Tips:

  - Keep it fun and interactive with immediate prize distributions.

  - Encourage attendees to purchase tickets throughout the event.

Cork Pull

- Setup:

  - Collect wine bottles (donated or purchased) with hidden values.

  - Attach a numbered cork to each bottle (matching to the prize).

- Execution:

  - Attendees purchase a cork for a fixed price (e.g., $25) and "pull" it to reveal their prize (which corresponds to a wine bottle).

  - Display bottles and create excitement around premium wine selections.

- Tips:

  - Have a variety of wine bottles and make the experience fun.

  - Offer an upscale bottle as a "grand prize."

5. Event Day Checklist

- Venue Preparation:

  - Set up the silent and live auction displays.

  - Create PowerPoint for event including all Sponsors and Donators.

  - Decorate according to the holiday theme.

  - Set up raffle and cork pull tables.

  - Test sound, lighting, and technology.

  - Designate staff/volunteers for registration, auctions, raffles, etc.

  - Ensure Square for raffle purchases is onsite and working.

- Check-in Process:

  - Greet guests and provide them with bid numbers and raffle tickets.

  - Set up a welcome desk with event details, auction catalogs, and a donation station.

- Live Event:

  - Host Welcome & Opening Remarks: Introduce the charity, auction items, and the schedule.

  - Silent Auction Opens: Announce the start time and encourage bidding.

  - Raffle Draws: Announce winners and distribute prizes.

  - Live Auction: Announce each item and engage the audience in bidding.

  - Cork Pull: Allow guests to purchase corks and “pull” to win wine bottles.

6. Post-Event Actions

Follow-Up:

- Thank You Notes: Send personalized thank-you messages to donors, volunteers, and guests.

- Final Fundraising Report: Announce the total amount raised.

- Social Media Post-Event Recap: Share photos and highlights from the event.

- Donor Acknowledgment: Ensure that auction winners and donors receive their prizes promptly.

7. Event Evaluation

- Post-Event Survey: Gather feedback from attendees, volunteers, and sponsors for improvements.

- Team Debrief: Discuss what worked well and areas to improve.

- Financial Review: Finalize and evaluate expenses vs. funds raised.

Final Thoughts

This playbook is meant to guide you in organizing a successful charity event. Each aspect of the event—silent and live auctions, raffles, and cork pulls—requires careful planning and attention to detail, but when done right, they can make for a memorable, engaging, and successful fundraising experience.